Software Project Management Plan

For

DATS CareHub

An AI-Integrated Digital Care Management System

Team 2

Winter 2026

Version 1.0

Team Members:

Devi Madhusudanan  (000489919)

Samuel Molla  (000499865)

Tanvi Tanvi  (000489679)

Alice Yu  (000488835)

Table of Contents

1.	Introduction	3

1.1	Project Overview	3

1.2	Goals and Objectives	3

2.	Start Plan	4

2.1	Team Organization	4

2.2	Development Tool Selection	5

3.	Work Plan	5

3.1	Project Tasks	5

3.2	Team Member Responsibilities	7

3.3	Gantt Chart	7

4.	Project Deliverables	8

4.1	Software	8

4.1.1	Backend API (CareHub.Api)	8

4.1.2	Desktop Application (CareHub.Desktop)	9

4.1.3	Web Application (CareHub.Web)	9

4.1.4	Mobile Application (CareHub.Mobile)	9

4.1.5	Shared Data & Infrastructure	9

4.1.6	Database Schema	10

4.2	User Guide	10

4.2.1	Getting Started	10

4.2.2	Authentication	10

4.2.3	Core Workflows	11

4.2.4	AI Features	11

4.2.5	Offline Mode (Desktop Only)	11

Revision History	11

# 1.	Introduction

## 1.1	Project Overview

DATS CareHub is an AI-integrated digital care management system designed for assisted living facilities, long-term care homes, and community care settings. The system centralizes resident information, medication administration records (MAR), clinical observations, medication inventory, and staff management into a single digital hub, replacing fragmented paper notes and disconnected software systems.

CareHub is a multi-platform solution consisting of:

Backend API: Built with ASP.NET Core 8.0, providing RESTful endpoints secured with JWT authentication and role-based access control (RBAC). Data is persisted in PostgreSQL 16, containerized via Docker Compose.

Desktop Application: Built with .NET MAUI targeting Windows 10/11, supporting offline-first operation with local JSON storage and automatic sync when connectivity is restored.

Web Application: Built with React 18 and Vite, providing browser-based access to the system for administrative and clinical workflows.

Mobile Application: Built with React Native 0.74.5 (migration in progress), targeting Android and iOS devices for bedside and on-the-go access.

The system also integrates AI-powered features via the Groq API (Llama 3.3 70B model) for clinical assistance, including shift summaries, medication explanations, trend detection, and natural language care queries. All AI features are assistive-only and require human review before action.

## 1.2	Goals and Objectives

Primary Goals:

Centralize Care Records – Unify resident profiles, medication records, observations, and staff data into a single, accessible platform.

Digitize Medication Administration – Replace paper-based MAR sheets with a digital workflow supporting statuses (Given, Refused, Held, Missed, Not Available), voiding with audit trails, and slot-based scheduling.

Enable Multi-Platform Access – Provide desktop (offline-capable), web, and mobile interfaces so staff can access and update records from any device.

Integrate AI Assistance – Offer AI-powered clinical insights (shift summaries, trend detection, medication info) while maintaining human oversight and data safety.

Ensure Security and Compliance – Implement JWT authentication, role-based access control, and BCrypt password hashing to protect sensitive health data.

Specific Objectives:

Implement full CRUD operations for residents, medications, observations, and staff.

Build a complete MAR workflow with batch recording, status tracking, and voiding capabilities.

Develop a medication inventory system with stock tracking, reorder alerts, and expiry management.

Implement a medication ordering workflow (Request → Order → Receive/Cancel).

Create an offline-first desktop application with automatic sync.

Integrate AI features with rate limiting (25 req/min global, 8 req/min per user) and safety disclaimers.

Support four user roles: Admin, Nurse, General CareStaff, and Observer.

# 2.	Start Plan

## 2.1	Team Organization

The team is organized into two sub-teams with overlapping responsibilities:

Team A – Core Systems & Backend (Alice + Samuel)

| Responsibility | Details |
| --- | --- |
| Database Design | PostgreSQL schema, EF Core migrations, seed data |
| API Development | ASP.NET Core 8.0 Web API, RESTful endpoints |
| Authentication & Authorization | JWT Bearer tokens, RBAC with 4 roles |
| MAR Logic & Workflow | Medication administration recording, voiding, reporting |
| Offline Sync Protocol | Idempotent sync via ClientRequestId, JSON local storage |
| AI Integration | Groq API service, rate limiter, prompt engineering |
| Technical Documentation | SDD, SRD, API documentation |

Team B – Web & Mobile Frontend (Devi + Tanvi)

| Responsibility | Details |
| --- | --- |
| React Web UI | Dashboard, resident management, MAR viewer, orders page |
| Admin Dashboard | Staff management, inventory overview, low-stock alerts |
| CRUD Forms | Resident, medication, observation, and staff forms |
| AI Dashboard UI | Shift summary, care query, medication explain interfaces |
| Styling & Navigation | Component-based architecture, responsive design |
| React Native Mobile | Migration from MAUI concepts to React Native (in progress) |

## 2.2	Development Tool Selection

| Category | Tool / Technology | Purpose |
| --- | --- | --- |
| Backend Framework | ASP.NET Core 8.0 | Web API development |
| ORM | Entity Framework Core 8.0 (Npgsql) | Database access and migrations |
| Database | PostgreSQL 16 | Primary data storage |
| Containerization | Docker / Docker Compose | Database container management |
| Desktop Framework | .NET MAUI | Windows desktop application (offline-first) |
| Web Framework | React 18.3.1 | Web-based user interface |
| Web Build Tool | Vite 5.4.10 | Frontend build and dev server |
| Mobile Framework | React Native 0.74.5 | Cross-platform mobile app |
| AI Provider | Groq API (Llama 3.3 70B) | AI-powered clinical assistance |
| Authentication | JWT Bearer Tokens + BCrypt | Secure auth and password hashing |
| Version Control | Git / GitHub | Source code management |
| CI/CD | GitHub Actions | Automated build pipeline |
| IDE | Visual Studio / VS Code | Code editing and debugging |
| API Testing | Swagger UI | Interactive API documentation and testing |
| Unit Testing | xUnit / NSubstitute | Backend unit tests |
| Languages | C# (.NET 8), JavaScript/JSX | Primary programming languages |

# 3.	Work Plan

## 3.1	Project Tasks

The project follows an iterative 5-week sprint plan with milestone-based deliverables:

Week 1 – Foundation & Authentication (M0 → M1)

| Task ID | Task | Description |
| --- | --- | --- |
| T1.1 | Project Setup | Initialize .NET solution, Docker Compose, PostgreSQL container |
| T1.2 | Database Schema Design | Design and implement EF Core entities and initial migration |
| T1.3 | JWT Authentication | Implement login endpoint, token generation, and middleware |
| T1.4 | Role-Based Access Control | Define roles (Admin, Nurse, CareStaff, Observer) and policies |
| T1.5 | Seed Data | Create JSON seed files for residents and medications |
| T1.6 | Desktop App Scaffold | Initialize .NET MAUI project with MVVM architecture |

Week 2 – Core CRUD Operations (M1 → M2)

| Task ID | Task | Description |
| --- | --- | --- |
| T2.1 | Residents API | CRUD endpoints for resident management |
| T2.2 | Medications API | CRUD endpoints with stock management and low-stock queries |
| T2.3 | Observations API | Create and query clinical observations |
| T2.4 | Staff Management API | Admin-only staff CRUD endpoints |
| T2.5 | Web UI Scaffold | Initialize React/Vite project, set up routing and API client |
| T2.6 | Desktop CRUD Pages | Implement resident and medication pages in MAUI |

Week 3 – MAR Workflow (M2 → M3)

| Task ID | Task | Description |
| --- | --- | --- |
| T3.1 | MAR Entry API | Create, query, and void MAR entries with idempotency |
| T3.2 | MAR Reporting | Reporting endpoint with summary statistics |
| T3.3 | Medication Orders API | Order lifecycle (Request → Order → Receive/Cancel) |
| T3.4 | Inventory Ledger | Automatic stock deduction on MAR administration |
| T3.5 | MAR Demo Seeder | 14-day demo data seeder for development |
| T3.6 | Web MAR Viewer | React page for viewing and interacting with MAR data |

Week 4 – Offline, Observations & AI (M3 → M4)

| Task ID | Task | Description |
| --- | --- | --- |
| T4.1 | Offline Storage | Local JSON persistence for desktop app |
| T4.2 | Sync Queue | Offline-to-online sync with conflict resolution |
| T4.3 | Groq AI Integration | AI service wrapper with rate limiting |
| T4.4 | AI Endpoints | Shift summary, medication explain, trend detection, care query |
| T4.5 | AI Dashboard UI | Web and desktop interfaces for AI features |
| T4.6 | Mobile App Scaffold | Initialize React Native project with navigation and auth |

Week 5 – Buffer & Polish (M4 → M5)

| Task ID | Task | Description |
| --- | --- | --- |
| T5.1 | Cross-Platform Testing | End-to-end validation across Desktop, Web, and Mobile |
| T5.2 | Role Cleanup | Align role constants across all controllers |
| T5.3 | UI Polish | Consistent styling, error handling, and UX improvements |
| T5.4 | Documentation | Finalize SDD, SRD, SPMP, and user guide |
| T5.5 | Bug Fixes | Address mismatch issues and regression testing |
| T5.6 | Deployment Preparation | CI/CD pipeline validation, configuration review |

## 3.2	Team Member Responsibilities

| Team Member | Primary Responsibilities |
| --- | --- |
| Alice Yu | Database schema, EF Core migrations, API controllers, JWT auth, AI integration, MAR workflow, audit logging |
| Samuel Molla | API development, offline sync protocol, React web UI, API client services, CI/CD pipeline |
| Devi Madhusudanan | React web pages (Dashboard, Residents, Observations), CRUD forms, styling, React Native mobile migration |
| Tanvi Tanvi | React web pages (Inventory, Staff, Orders), admin dashboard, AI dashboard UI, React Native mobile screens |

## 3.3	Gantt Chart

The following table represents the project timeline across 5 weeks:

| Task | Week 1 (M1) | Week 2 (M2) | Week 3 (M3) | Week 4 (M4) | Week 5 (M5) |
| --- | --- | --- | --- | --- | --- |
| Project Setup & DB Schema | ███ |  |  |  |  |
| JWT Auth & RBAC | ███ |  |  |  |  |
| Seed Data & Desktop Scaffold | ███ |  |  |  |  |
| Residents API |  | ███ |  |  |  |
| Medications API |  | ███ |  |  |  |
| Observations & Staff API |  | ███ |  |  |  |
| Web UI Scaffold & Desktop CRUD |  | ███ |  |  |  |
| MAR Entry API & Reporting |  |  | ███ |  |  |
| Medication Orders API |  |  | ███ |  |  |
| Inventory Ledger & MAR Seeder |  |  | ███ |  |  |
| Web MAR Viewer |  |  | ███ |  |  |
| Offline Storage & Sync |  |  |  | ███ |  |
| Groq AI Integration |  |  |  | ███ |  |
| AI Endpoints & Dashboard |  |  |  | ███ |  |
| Mobile App Scaffold |  |  |  | ███ |  |
| Cross-Platform Testing |  |  |  |  | ███ |
| UI Polish & Bug Fixes |  |  |  |  | ███ |
| Documentation & Deployment |  |  |  |  | ███ |

# 4.	Project Deliverables

## 4.1	Software

The CareHub system delivers the following software components:

### 4.1.1	Backend API (CareHub.Api)

| Component | Description |
| --- | --- |
| REST API | ASP.NET Core 8.0 Web API with 30+ endpoints |
| Authentication | JWT Bearer token authentication with 120-minute expiry |
| Authorization | Role-based access control (Admin, Nurse, CareStaff, Observer) |
| Database | PostgreSQL 16 with EF Core migrations and seed data |
| AI Service | Groq API integration with rate limiting and safety controls |
| Health Check | /health endpoint for monitoring |
| Swagger | Interactive API documentation at /swagger |

API Endpoint Summary:

| Module | Endpoints |
| --- | --- |
| Authentication | POST /api/auth/login, GET /api/auth/me |
| Residents | GET/POST/PUT/DELETE /api/residents |
| Medications | GET/POST/PUT/DELETE /api/medications, stock adjustment, low-stock query |
| Observations | GET/POST /api/observations, by-resident queries |
| MAR | GET/POST /api/mar, void, report, seed-demo |
| Medication Orders | GET/POST/PUT/DELETE /api/medicationorders, status updates |
| Staff | GET/POST/PUT/DELETE /api/staff (Admin only) |
| AI | Shift summary, medication explain, trend detection, care query, handoff |

### 4.1.2	Desktop Application (CareHub.Desktop)

| Feature | Description |
| --- | --- |
| Platform | .NET MAUI, Windows 10/11 only |
| Architecture | MVVM pattern with dependency injection |
| Pages | 34 XAML pages covering all clinical and admin workflows |
| Offline Mode | Local JSON storage with sync queue for offline-to-online reconciliation |
| Key Modules | Residents, Medications, MAR, Observations, Inventory, Staff, AI, Reports |

### 4.1.3	Web Application (CareHub.Web)

| Feature | Description |
| --- | --- |
| Platform | React 18.3.1 with Vite 5.4.10 |
| Architecture | Component-based with centralized API client |
| Key Pages | Dashboard, Residents, Observations, Inventory, Staff, MAR, Orders, AI |
| Requirement | Network connectivity required (no offline mode) |

### 4.1.4	Mobile Application (CareHub.Mobile)

| Feature | Description |
| --- | --- |
| Platform | React Native 0.74.5 (Android/iOS) |
| Status | Migration in progress (scaffold phase) |
| Navigation | Bottom tabs + native stack (React Navigation 6.x) |
| Storage | AsyncStorage for local persistence |
| Access Control | Role-based screen access |

### 4.1.5	Shared Data & Infrastructure

| Component | Description |
| --- | --- |
| Seed Data | 16 residents, 115 medications, sample observations (JSON files) |
| Docker Compose | PostgreSQL 16 container with persistent volume |
| CI/CD | GitHub Actions workflow (build.yml) for automated builds |
| Unit Tests | xUnit tests for AI rate limiter, Groq service, and MAR seeder |

### 4.1.6	Database Schema

The system uses 7 core entities:

| Entity | Key Fields |
| --- | --- |
| Resident | Demographics, address, emergency contacts, doctor info, allergies, room placement |
| Medication | Name, dosage, stock quantity, reorder level, expiry date, weekly schedule |
| MarEntry | Resident/medication link, status, dose, timestamps, void support, audit trail |
| Observation | Resident link, type (BP/Temp/Note), value, recorded by staff |
| MedicationOrder | Status workflow, timestamps, staff sign-offs, quantity, notes |
| MedicationInventoryLedger | Stock changes, reason tracking, audit timestamps |
| AppUser | Username, password hash, display name, role, optional resident link |

## 4.2	User Guide

### 4.2.1	Getting Started

Prerequisites: Docker Desktop, .NET 8.0 SDK, Node.js 18+, Git

- Database Setup: Run "docker compose up -d" to start the PostgreSQL container.

- Apply Migrations: Run "dotnet ef database update --project CareHub.Api" to create the database schema.

- Configure API: Copy appsettings.json to appsettings.Development.json and add the Groq API key.

- Start API: Run "dotnet run --project CareHub.Api" (available at http://localhost:5001).

- Start Desktop: Run "dotnet run --project CareHub.Desktop" in a separate terminal.

- Start Web: Run "cd CareHub.Web && npm install && npm run dev" for the web interface.

### 4.2.2	Authentication

Login using the provided test accounts:

| Username | Password | Role | Access Level |
| --- | --- | --- | --- |
| admin | admin123 | Admin | Full system access including staff management |
| nurse1 | nurse123 | Nurse | Clinical access to MAR, observations, medications, orders |
| carestaff1 | care123 | General CareStaff | Limited clinical access, primarily observations |
| resident1 | resident123 | Observer | Read-only, restricted to own resident record |

### 4.2.3	Core Workflows

Resident Management: Add, edit, view, and delete resident profiles with full demographics, allergies, and emergency contact details.

Medication Administration (MAR): Record medication administration with status tracking (Given, Refused, Missed, Not Available), batch recording by time slot, and voiding with audit trail.

Observations: Log vital signs (blood pressure, temperature) and clinical notes linked to specific residents.

Medication Inventory: Track stock levels, receive low-stock alerts, manage expiry dates, and process medication orders through the Request → Order → Receive workflow.

Staff Management: (Admin only) Create and manage staff accounts with role assignments.

### 4.2.4	AI Features

CareHub integrates AI-powered clinical assistance features:

Shift Summary: Generate an AI-powered 24-hour summary for any resident.

Medication Explain: Get AI-generated reference information about medications including side effects and usage.

Detect Trends: Analyze 14 days of vitals and compliance data for patterns.

Care Query: Ask natural language questions about residents and medications.

Shift Handoff: Generate a facility-wide handoff summary for shift changes.

Important: All AI outputs include safety disclaimers and require human review before any clinical action is taken. AI features are assistive-only and do not modify data autonomously.

### 4.2.5	Offline Mode (Desktop Only)

The desktop application stores data locally in JSON format when offline.

Changes are queued and automatically synced when connectivity is restored.

MAR entries use idempotent ClientRequestIds to prevent duplicate submissions during sync.

# Revision History

| Version | Date | Name | Description |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | Team 2 | Initial Document |